## Sheet1
Creighton University - ADA Report for 2011/2012
WorkOrder# | Status | Description | Building | M or P | Cost
1201788 | Completed | Sidewalk replacement for ADA | BIC | P | 16887
1231233 | Completed | ADA Assessment | Campus | P | 1219.94
1215502 | Completed | Make restroom accessible | Old Gym | P | 4150
1220628 | Completed | ADA access sign for North parking lot | Murphy Building | P | 54.9
1213196 | Completed | Purchase ADA Compliance Guide | Jelinek Building | P | 438.5
1218373 | Completed | Design for exterior elevator | St. John's Church | P | 15078.37
1210771 | Completed | Fire protection and voice evacuation | Criss I | P | 72678.16
1200793 | Completed | Replace handicap curbing in front of building | Kitty Gaughn | M | 2966.35
1234292 | Completed | Repair handicap fountain outside 4003C | Harper Center | M | 33.65
1226233 | Completed | Plumbing repairs in ADA Room 413 | Swanson Hall | M | 33.65
113540.52
1140232 | In Progress | Voice evacuation upgrade | Kiewit Fitness Cntr | P | 81400
1140233 | In Progress | Fire protection system | Kiewit Fitness Cntr | P | 59070
1227018 | In Progress | Fire protection and voice evacuation | Swanson Hall | P | 213900
354370
1229659 | In Design/Pricing | ADA ACCESS | Murphy Building | P
1225200 | In Design/Pricing | Remodel 1st floor with new ADA entrance | Hitchcock/CommArts | P
1209159 | Pending Approval | Modify South entry doors to make accessible | Alumni Library | P | 20303
1220860 | Pending Approval | Clinic remodel | Florence Clinic | P | 159999
180302
911993 | On Hold | Handicap access East side; card access | Psy Clinic | P
923927 | On Hold | Parking stall lacks signage | BIC | P
923928 | On Hold | Signage for inaccessible entrances | BIC | P
923929 | On Hold | Elevator jams lack signage | BIC | P
1014236 | On Hold | Threshold at entry door | ROTC | P
1124555 | On Hold | ADA ramp West side; card access | Psy Clinic | P
1202514 | Cancelled | Replace deterioate concrete - ADA approach | P26 | P
Projects Completed with ADA elements in the design
1045785 | Completed | Classroom124 upgrade | Law School | P | 255408.99
| ADA design elements for renovation to existing facilities | ADA design elements for renovation to existing facilities
| Review building and renovation site for potential barriers and develop solutions. General items to consider when developing the design for renovation: | Exterior: Accessible entrance - at least one route of travel should be safe and accessible for everyone, including people with disabilities. is at least 36" wide is there adequate accessible parking does route have curb cuts at drives proper ramps not greater than 1:20 slope is the threshold 1/4" or less
| Exterior | Interior Access to goods and service - accessible horizontal and vertical circulation such as: 5" circle or T-shape space for wheelchair movement door widths with 18" clear space next to handle thresholds 1/4" or less emergency lights and signals elevators Other items - such as useable restrooms for people with disabilities corridor widths signage drinking fountains/heights seating - counter heights non-slip surfaces do objects along routes protrude more than 4"
Note: A total of 67 signage requests were processed in the fiscal year 2011/2012. Of which 50% met the ADA requirements. The other 50% consisted of parking signs, vinyl on glass, or engraved type signage.
Purchasing Department ADA Acquisitions
|  | Nothing to report this fiscal year. |  |  | 0