# Creighton University

2010/2011 Operating Budget Schedule – Condensed

(Refer to Detailed Schedule Attached)

| Activity |  | Person Responsible | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Discuss 2010/11 budget issues, priorities, process and schedule. | Budget Committee | Week of August 24 |
| 2 | Distribute initial information request package to VPs and Deans (FTEs, program and expense requests, revenue estimates, etc.). | Budget Director | Week of August 31 |
| 2a | Meet with President’s Cabinet to discuss budget issues and get feedback. | President, VP Admin & Finance | September 16 |
| 3 | Complete estimates of enrollment, revenue estimates, prioritized expense requests, and other budget information. Submit to Budget Director. | Vice Presidents, Deans, Directors | October 9 |
| 4 | Review and summarize all submitted information, run models and review with Budget Committee. | Budget Director | Week of November 16 |
| 5 | Approve the following for the School of Medicine: salary pool increase, non-salary increase, benefit increase and tuition rate. | Budget Committee | Week of November 16 |
| 6 | Provide Medicine with “estimated” overhead allocation to schools and its “estimated” 2010/11 budget target. | Budget Director | December 1 |
| 7 | Present proposed tuition range increase and other budget highlights to University Board of Directors. | President | December 7 |
| 8 | Review, discuss, and finalize tuition, fee, and board and room increase, other revenue, salary pool rate increase, expense requests and guidelines, suggested budget issues & themes from the Financial Advisory Committee and any reductions or reallocations to arrive at an approved GCF bottom line. | Budget Committee | Between December 7 & February 8 |
| 9 | Meet with President’s Cabinet to update them on budget process and get feedback. | President, VP Admin & Finance | December 9 |
| 9a | Meet with President’s Cabinet to review approved budget guidelines, increases and new expenses. | President, VP Admin & Finance | February 17 |
| 10 | Prepare summary of approved expense guidelines, tuition rate and revenue and expense highlights. | Budget Director | February 19 |
| 11 | Distribute budget targets, forms and instructions to all areas. | Budget Director | February 19 |
| 12 | Prepare detailed budgets. (Due dates are staggered). | Vice Presidents, Deans, Directors | March 19, March 26, April 2 |
| 13 | Present any pertinent information to the Board of Directors. | President | March 1 |
| 14 | Review detailed budgets and prepare summary reports for Budget Committee and Board of Directors. | Budget Director | Week of May 10 |
| 15 | Present annual operating plan and budget to the University Board of Directors. | President & VP Admin & Finance | June 7 |
| 16 | Approve final operating plan and budget. | Board of Directors | June 7 |