Creighton University

2009/2010 Operating Budget Schedule - Detailed

| Activity | Person Responsible | Expected Completion Date |
| --- | --- | --- |
| 1 | Request overhead allocation statistics from appropriate departments. | Budget Office | August 15 |
| 2 | Budget Committee meets to discuss: 2009/10 Budget Process schedule 2009/10 operating priorities and issues. Strategic plan priorities (if available) | Budget Committee | Week of August 18 |
| 3 | Distribute to the Vice Presidents and Deans: Summary of key budget issues and priorities for 2009/10. Revenue Budget initial information request package which includes: Estimated student, faculty and staff headcount and FTEs. (Schedule 1) Estimate of various revenue items other than tuition. (Schedule 2) Tuition increase recommendations (Dean’s only). Endowment Income (Associate VP for Finance only). Gift Income (VP University Relations only). Completion instructions. Expense Budget initial information request package which includes: New expense requests. (New requests should relate to the University’s Strategic Plan.) (Schedules 3 &/or 3VP) Scholarships and remissions (Enrollment Management, Athletics, Schools). Employee benefits increase range (Controller and Human Resources only). Salary pool rate increase recommendation (Human Resources). Transfer budget change summary includes any 2009/10 scheduled or estimated changes to existing transfers. (Schedule 4) New program requests. (Schedule 5) | Budget Director | Week of September 1 |
| 4 | Complete requested overhead allocation statistics and send to the Budget Office. | Select Departments | September 15 |
| 5 | Complete requested budget information (4c through 4f). VPs review with subordinates and send approved information to Budget Director. | Vice Presidents, Deans, Directors | October 13 |
| 6 | Prepare summary of items for potential reduction or reallocation from existing operating budget: one-time expenses; ending debt; fixed term programs or expenses which expire at year-end; etc. | Budget Director | October 27 |
| 7 | Request preliminary revenue and expense outline with assumptions based on enrollment estimates from Residence and Dining, Student and Fitness Centers. (Provide them with headcounts and estimated salary, benefit and non-salary increase percentages.) | Budget Director | October 27 |
| Activity | Person Responsible | Expected Completion Date |
| 8 | Review estimated student FTEs and head counts, revenue projections, new program, expense requests, and other items from Step 4. | Budget Director | November 10 |
| 9 | Prepare employee benefit dollar estimate. Review with Budget Director and VP for Administration and Finance. | Controller | November 10 |
| 10 | Review all expense, and program requests: Classify the expense and program requests into multi-year or one-year operating requests. Review linkage of the expense requests to University operating and strategic plan priorities for the budget year. Prepare an analysis of funds available for operating and strategic expense requests and essential capital requests. Prepare a report for the Budget Committee that summarizes and compares the amounts requested to the funds available. | Budget Director | November 10 |
| 11 | Prepare and distribute an information book to the Budget Committee that summarizes the results of the model, student FTEs, revenue estimates, expense, program requests, budget issues and other gathered information. | Budget Director | Week of November 17 |
| 12 | Review the following with the Budget Committee: Projected student FTEs. Other projected revenue. New expense and program requests. (Includes strategic plan objective implementation.) Salary pool rate increase recommendation from HR. Budget issues. “Funds Available/Funds Requested” summary. Benefit plan estimates. Current budget model highlights. | Budget Director | Week of November 17 |
| 13 | Approve the following for the School of Medicine: salary pool increase, non-salary increase, benefit increase and tuition rate. | Budget Committee | Week of November 17 |
| 14 | Vice Presidents present expense, program and capital requests, and related information before the Budget Committee. | Vice Presidents | Week of November 30 |
| 15 | Compute “estimated” overhead allocation to schools and “estimated” 2009/10 GCF target for School of Medicine. | Budget Office | November 30 |
| 16 | Provide “estimated” overhead allocation and Medicine’s “estimated” 2009/10 GCF target to the School of Medicine. | Budget Office | December 1 |
| 17 | Medicine begins preparation for 2009/10 school budget targets with estimated overhead and target | Medical Dean’s Office | December 1 |
| 18 | Present proposed tuition range and other budget highlights to University Board of Directors. | President | December 1 |
| 19 | Approve proposed range of tuition rate increase. | Board of Directors | December 1 |
| 20 | Send preliminary revenue and expense outlines and assumptions for Resident and Dining, Student and Fitness Center to Budget Office for incorporation into the Budget Model. | VP Student Services | December 1 |
| 21 | Collect additional information as required by the Budget Committee for new revenue, expense, new program requests, or other information. | Budget Director | December 1 |
| 22 | Update as necessary: Budget issues “Funds Available/Funds Requested” summary. | Budget Director | December 1 |
| Activity | Person Responsible | Expected Completion Date |
| 23 | Meet as necessary to arrive at an approved University bottom line. Discuss and finalize: Tuition, University fee and board and room rate increases and all other revenue. Financial aid increase. Salary and non-salary increase percentage guidelines. New expense requests (including costs of Strategic Plan implementation). Capital acquisition impact on operating budget. New program requests (if applicable). Activities, programs, or other items for potential reduction, elimination or reallocation. Reduction or elimination of expenses related to certain items in operating budgets. | Budget Committee | December 8 through February 9 |
| 24 | Medicine distributes its school targets and medical departments begin detail budget preparation. | Medical Dean’s Office/Medical School Departments | January 5 |
| 25 | Meet with the President’s Cabinet to review: tuition fee increase, board and room increase, approved new expense and new program requests linked to prioritized University objectives, approved salary and tuition increases, budget targets, and all other pertinent information. | President, VP Administration and Finance | Week of February 16 |
| 26 | Update the budget model for new revenue, expenses and other decisions approved by the Budget Committee to arrive at the approved University budget outline and bottom line. | Budget Director | February 18 |
| 27 | Prepare summary of approved expense guidelines, tuition rate and revenue and expense highlights and general University revenue distribution. | Budget Director | February 18 |
| 28 | Distribute detailed budget package to Vice Presidents, Deans and Directors, which includes forms and instructions; budget targets. | Budget Director | February 18 |
| 29 | Prepare detailed department budgets by month using approved targets and guidelines. Review with Vice Presidents. (Due dates staggered into three groups.) | Deans & Dept. Managers (Admin. Departments) Medicine only) (All Other Schools) | March 5 –April 3 March 5 – TBA March 5 – April 10 |
| 30 | Review detailed preliminary department budgets and submit to Budget Director. (Due dates staggered into three groups.) | Vice Presidents | April 3 April l0 TBA |
| 31 | Present to the Board of Directors proposed tuition rate, new revenue and expenses, and other relevant budget highlights and information. | President | March 2 |
| 32 | Review submitted budgets, correct errors, resolve any issues, and load details into financial system “Holding Tank.” | Budget Director | March 23 - May 4 |

| Activity | Person Responsible | Expected Completion Date |
| --- | --- | --- |
| 33 | Prepare preliminary presentation slides and summaries for the 2009/10 operating budget. Review with VP Admin & Finance for presentation to Academic Council. | Budget Director | Week of April 23 |
| 34 | Distribute the detailed budget printouts and summaries of corrections to the budget preparers of the schools and departments as budget reviews are completed. | Budget Director | March 25 – May 5 |
| 35 | Prepare final presentation slides, notes and summaries for the 2009/10 operating budget. | Budget Director | May 11 |
| 36 | Review budget summary and highlights with the President’s Cabinet and then the Chairman of the Finance Committee of the Board of Directors. | VP Admin & Finance | Week of May 11 |
| 37 | Prepare additional notes and other information as needed for the Board presentation by the VP Administration and Finance. | Budget Director | May 11 to May 29 |
| 38 | Present annual operating plan and budget to the University Board of Directors. | President and VP Admin & Finance | June 1 |
| 39 | Approve final operating plan and budget. | Board of Directors | June 1 |
| 40 | Load detailed budget data into the University financial system once approved by the Board of Directors. | Budget Director & Controller | Week of June 15 |
| 41 | Implement the annual operating budget (begin managing with the new budget). | Dept. Managers | July 1 |