# Creighton University

2010/2011 Operating Budget Schedule - Detailed

| Activity |  | Person Responsible | Expected Completion Date |
| --- | --- | --- | --- |
| 1 | Request overhead allocation statistics from appropriate departments. | Budget Office | August 17 |
| 2 | Budget Committee meets to discuss: - 2010/11 Budget Process schedule and process. - 2010/11 operating priorities and issues. - Strategic plan priorities (if available) | Budget Committee | Week of August 24 |
| 3 | Distribute to the Vice Presidents and Deans: - Summary of key budget issues and priorities for 2010/11. - Revenue Budget initial information request package which includes: - Estimated student, faculty and staff headcount and FTEs. (Schedule 1) - Estimate of various revenue items other than tuition. (Schedule 2) - Tuition increase recommendations (Dean’s only). - Endowment Income (Associate VP for Finance only). - Gift Income (VP University Relations and Athletics only). - Completion instructions. - Expense Budget initial information request package which includes: - New expense requests. (New requests should relate to the University’s Strategic Plan.) (Schedules 3 &/or 3VP) - Discounted and funded scholarships and remissions (Enrollment Management, Athletics). - Employee benefits increase range (Controller and Human Resources only). - Salary pool rate increase recommendation (Human Resources). - Transfer budget change summary includes any 2010/11 scheduled or estimated changes to existing transfers. (Schedule 4) - New program requests. (Schedule 5) - Direct School managed scholarships (Schedule 6) (Schools only). | Budget Director | Week of August 31 |
| 4a | Meet with President’s Cabinet to discuss 2010/2011 budget issues and get feedback. | President, VP Admin & Finance | September 16 |
| 4b | Complete requested overhead allocation statistics and send to the Budget Office. | Select Departments | September 18 |
| 5 | Complete requested budget information (3b through 3f). VPs review with subordinates and send approved information to Budget Director. | Vice Presidents, Deans, Directors | October 9 |
| 6 | Prepare summary of items for potential reduction or reallocation from existing operating budget: one-time expenses; ending debt; fixed term programs or expenses which expire at year-end; etc. | Budget Director | October 26 |

| Activity |  | Person Responsible | Expected Completion Date |
| --- | --- | --- | --- |
| 7 | Request preliminary revenue and expense outline with assumptions based on enrollment estimates from Residence and Dining, Student and Fitness Centers. (Provide them with headcounts and estimated salary, benefit and non-salary increase percentages.) | Budget Director | October 26 |
| 8 | Review estimated student FTEs and head counts, revenue projections, new program, expense requests, and other items from Step 3. | Budget Director | November 10 |
| 9 | Prepare employee benefit dollar estimate. Review with Budget Director and VP for Administration and Finance. | Controller | November 10 |
| 10 | Review all expense, and program requests: - Classify the expense and program requests into multi-year or one-year operating requests. - Review linkage of the expense requests to University operating and strategic plan priorities for the budget year. - Prepare an analysis of funds available for operating and strategic expense requests and essential capital requests. - Prepare a report for the Budget Committee that summarizes and compares the amounts requested to the funds available. | Budget Director | November 10 |
| 11 | Prepare and distribute an information book to the Budget Committee that summarizes the results of the model, student FTEs, revenue estimates, expense and program requests, budget issues and other gathered information. | Budget Director | Week of November 16 |
| 12 | Review the following with the Budget Committee: - Projected student FTEs. - Other projected revenue. - Discounted and funded aid estimate. - New expense and program requests. (Includes strategic plan objective implementation.) - Salary pool rate increase recommendation from HR. - Budget issues. - “Funds Available/Funds Requested” summary. - Benefit plan estimates. - Current budget model highlights. | Budget Director | Week of November 16 |
| 13 | Approve the following for the School of Medicine: salary pool increase, non-salary increase, benefit increase and tuition rate. | Budget Committee | Week of November 23 |
| 14 | Compute “estimated” overhead allocation to schools and “estimated” 2010/11 GCF target for School of Medicine. | Budget Office | November 30 |
| 15 | Provide “estimated” overhead allocation and Medicine’s “estimated” 2010/11 GCF target to the School of Medicine. | Budget Office | December 1 |
| 16 | Medicine begins preparation for 2010/11 school budget targets with estimated overhead and target | Medical Dean’s Office | December 1 |
| 17 | Present proposed tuition range and other budget highlights to University Board of Directors. | President | December 7 |
| 18 | Approve proposed range of tuition rate increase. | Board of Directors | December 7 |
| 19 | Send preliminary revenue and expense outlines and assumptions for Resident and Dining, Student and Fitness Center to Budget Office for incorporation into the Budget Model. | VP Student Services | December 7 |

| Activity |  | Person Responsible | Expected Completion Date |
| --- | --- | --- | --- |
| 20 | Collect additional information as required by the Budget Committee for new revenue, expense, new program requests, or other information. | Budget Director | December 7 |
| 21 | Update as necessary: - Budget issues - “Funds Available/Funds Requested” summary. | Budget Director | December 7 |
| 22 | Meet as necessary to arrive at an approved University bottom line. Discuss and finalize: - Tuition, University fee and board and room rate increases and all other revenue. - Financial aid increase. - Salary and non-salary increase percentage guidelines. - New expense requests (including costs of Strategic Plan implementation). - Capital acquisition impact on operating budget. - New program requests (if applicable). - Expansion of existing programs. - Activities, programs, or other items for potential reduction, elimination or reallocation. - Reduction or elimination of expenses related to certain items in operating budgets. | Budget Committee | December 7 through February 8 |
| 22a | Meet with President’s Cabinet to update them on budget progress to date and get feedback. | President, VP Admin & Finance | December 9 |
| 23 | Medicine distributes its school targets and medical departments begin detail budget preparation. | CFO of CMA/Medical Dean’s Office | January 4 |
| 24 | Meet with the President’s Cabinet to review: tuition fee increase, board and room increase, approved new expense and new program requests linked to prioritized University objectives, approved salary and tuition increases, budget targets, and all other pertinent information. | President, VP Administration and Finance | Week of February 17 |
| 25 | Update the budget model for new revenue, expenses and other decisions approved by the Budget Committee to arrive at the approved University budget outline and bottom line. | Budget Director | February 19 |
| 26 | Prepare summary of approved expense guidelines, tuition rate and revenue and expense highlights and general University revenue distribution. | Budget Director | February 19 |
| 27 | Distribute detailed budget package to Vice Presidents, Deans and Directors, which includes forms and instructions; budget targets. | Budget Director | February 19 |
| 28 | Present to the Board of Directors proposed tuition rate, new revenue and expenses, and other relevant budget highlights and information. | President | March 1 |
| 29 | Prepare detailed department budgets by month using approved targets and guidelines. Review with Vice Presidents. (Due dates staggered into three groups.) | Deans & Dept. Managers (Admin. Departments) (4 weeks to complete) (Medicine only) (17 weeks from Dec 1 to complete) (All Other Schools) (6 weeks to complete) | March 19 March 26 April 2 |

| Activity |  | Person Responsible | Expected Completion Date |
| --- | --- | --- | --- |
| 30 | Review detailed preliminary department budgets and submit to Budget Director. (Due dates staggered into three groups.) | Vice Presidents | March 19 March 26 April 2 |
| 31 | Review submitted budgets, correct errors, resolve any issues, and load details into financial system “Holding Tank.” | Budget Director | March 26 - May 3 |
| 32 | Distribute the detailed budget printouts and summaries of corrections to the budget preparers of the schools and departments as budget reviews are completed. | Budget Director | March 26 – May 3 |
| 33 | Prepare final presentation slides, notes and summaries for the 2010/11 operating budget. | Budget Director | May 10 |
| 34 | Review budget summary and highlights with the President’s Cabinet and then the Chairman of the Finance Committee of the Board of Directors. | VP Admin & Finance | Week of May 10 |
| 35 | Prepare additional notes and other information as needed for the Board presentation by the VP Administration and Finance. | Budget Director | May 10 to June 4 |
| 36 | Present annual operating plan and budget to the University Board of Directors. | President and VP Admin & Finance | June 7 |
| 37 | Approve final operating plan and budget. | Board of Directors | June 7 |
| 38 | Load detailed budget data into the University financial system once approved by the Board of Directors. | Budget Director & Controller | Week of June 14 |
| 39 | Implement the annual operating budget (begin managing with the new budget). | Dept. Managers | July 1 |