## Shared Services
Creighton University VP of Finance
FY 13 Closing Timeline
2013-05-21 15:46
| Person Responsible | Finance Directors | Target
Begin planning meetings with Finance Directors | All | Finance Directors | 2013-05-20
A/P staff planning meeting | Katie |  | 2013-05-20
Campus notification of closing dates (Banner Finance listserv, CUBuyplus active users and web) | Linda |  | 2013-05-20
Petty Cash Confirmation Memos sent (confirm 5/31 balances) | Leisha | Finance Directors | 2013-05-24
Clone PROD to BAN8 | Helena | Doit | 2013-05-25
Inventory and Cash Wash reminders sent - We will confirm inventory as of June 21, NOT June 28 | Leisha | Finance Directors | 2013-05-29
Preliminary Schedule of Federal Financial Assistance (as of April) | Suzanne |  | 2012-05-29
No more ELIQs for opens and standing on GCF/UDF funds | Katie |  | 2013-06-01
Meeting with Jody Lange about outstanding legal bills | Linda |  | 2013-06-01
Preliminary audit work (through 6-21-11) including SFA Audit | All | Finance Directors | 2012-06-03
Complete Recurring Purchase Orders (Purchasing) | Katie |  | Ongoing
Cost Bi-weekly 12 Payroll | Goldie/Suzanne | Payroll | 2013-06-10
TBAN GL Roll test | Michon/Suzanne | Doit | 2013-06-14
TBAN Encumberance Roll Test | Suzanne | Doit | 2013-06-18
Biweekly 13 Pay Date | Goldie | Payroll | 2013-06-21
Start New FY Runs | Doit | Doit | 2013-06-21
Cost Biweekly 13 Payroll | Goldie/Suzanne | Payroll | 2013-06-24
TBAN Budget Roll Test
Mastercard cycle closes | Jerrod | Finance Directors | 2012-06-24
Retrofits/TERs to Business Service Center - Assume 2 days mail time - Anything after this will be accrued | A/P | Finance Directors | 2013-06-26
P-Card Receipts to BSC (final day) | Jerrod M | Finance Directors | 2013-06-27
GL Roll | Michon/Suzanne | Doit | 2013-06-28
P-Card Approvals done | All | Finance Directors | 2013-06-28
G/L Roll | Michon |  | 2012-06-28
Switch old/new FY | Doit | Doit | 2013-06-29
Do not file invoices greater than $100,000 |  |  | n/a
PO Batch Close Process | Suzanne | Doit | 2013-06-30
Encumbrance Roll | Suzanne | Doit | 2013-06-30
Monthly 7 Paydate | Goldie | Payroll | 2013-07-01
Cost Monthly 7 | Suzanne/Goldie | Payroll | 2013-07-02
Cash deposit cutoff | Pam |  | 2012-07-02
All Receiving for June Completed in CUBuyplus | All | Finance Directors | 2013-07-02
Journal entries to Accounting Services- by noon | Michon | Finance Directors | 2012-07-03
Biweekly 14 Pay Date | Goldie | Payroll | 2013-07-05
Cost Biweely 14 | Suzanne/Goldie | Payroll | 2013-07-05
FPC Pay Date | Goldie | Payroll | 2013-07-05
Cost FPC 7 | Leisha | Payroll | 2013-07-05
Accrual entries from BSC - Items In CUBuyplus | Katie/Linda | Finance Directors | 2013-07-05
Accrual entries from departments - end of day | Leisha | Finance Directors | 2013-07-08
2nd payroll interface for monthly payroll for adjustments as needed | Suzanne/Goldie | Payroll | 2013-07-08
Finish Plant funds entries | Susan and Michon |  | 2013-07-08
Run PTO Carryforward | Cathy Harrahill | Payroll | 2013-07-08
Close Period 12 | Michon | Finance Directors | 2012-07-09
Run Preliminary reports | All | Finance Directors | 2012-07-09
CRUOPAL daily begins | Automatic | Doit | 2013-07-09
Between 12 and 14 fixes | Doit | Doit | 2013-07-09
Update fringe tables for new rates | Cathy H/Goldie | Payroll | 2013-07-12
Begin Biweekly 15 Run | Goldie | Payroll | 2013-07-15
Biweekly 15 Pay Date | Goldie | Payroll | 2013-07-19
Material journal entries (except FPC entry from Ray) to Michon by EOD - will post to period 14 | Michon | Finance Directors | 2013-07-17
FPC Journal Entries to Accounting Services – by noon. | Ray |  | 2013-07-19
TBAN Budget Roll Test | Michon or Suzanne | Doit | 2013-07-24
Before Final 14 Fixes | Suzanne | Doit | 2013-07-25
Close period 14 | Michon | Finance Directors | 2013-07-25
After Final 14 Fixes | Suzanne | Doit | 2013-07-25
Budget Roll | Suzanne or Michon | Doit | 2013-07-29
Biweekely 16 Pay Date | Goldie | Payroll | 2013-08-02
Cost Biweekly 16 | Suzanne/Goldie | Payroll | 2013-08-05
Close period 1 in FY 14 | Michon |  | 2013-08-08
Prior Yr Daily -- Weekly | Michon or Suzanne | Doit | 2013-08-23
Start final audit work (through 9-23-11) |  | Finance Directors | 2012-08-26
Turn off prior yr | Michon or Suzanne | Doit | 2013-10-01
CRUOPAL daily ends $bansruns/cruopal.run | Michon or Suzanne | Doit | 2013-10-01
Drop oldest CRUOPAL fy $(Banrpts)/bld CRUOPAL.shl | Michon or Suzanne | Doit | 2013-10-01
Board Meeting |  |  | November