## Shared Services
Creighton University VP of Finance
FY 14 Closing Timeline
2014-06-04 09:10
| Person Responsible | Finance Directors | Target
Begin planning meetings with Finance Directors | All | Finance Directors | 2014-05-07
A/P staff planning meeting | Katie |  | 2014-05-19
Campus notification of closing dates (Banner Finance listserv, CUBuyplus active users and web) | Linda |  | 2014-05-19
Petty Cash Confirmation Memos sent (confirm 5/31 balances) | Leisha | Finance Directors | 2014-05-23
Inventory reminders sent - We will confirm inventory as of June 20 | Leisha | Finance Directors | 2014-05-28
Preliminary Schedule of Federal Financial Assistance (as of April) | Suzanne |  | 2014-05-28
Blanket orders for FY15 to BSC | All |  | 2014-06-02
No more requests to close existing blankets | Katie |  | 2014-06-02
Meeting with Jody Lange about outstanding legal bills | Linda |  | 2014-06-02
Preliminary audit work (through 6-20-14) including SFA Audit | All | Finance Directors | 2012-06-02
Cost Bi-weekly 12 Payroll | Goldie/Suzanne | Payroll | 2014-06-06
Clone PROD to BAN8 | Helena | Doit | 2014-06-15
BAN8 GL Roll test | Michon | Doit | 2014-06-16
BAN8 Encumberance Roll Test | Suzanne | Doit | 2014-06-19
Biweekly 13 Pay Date | Goldie | Payroll | 2014-06-20
Start New FY Runs | Doit | Doit | 2014-06-20
Cost Biweekly 13 Payroll | Goldie/Suzanne | Payroll | 2014-06-23
P-Card cycle closes | Jerrod | Finance Directors | 2014-06-24
Retrofits/TERs to Business Service Center - Assume 2 days mail time - Anything after this will be accrued | A/P | Finance Directors | 2014-06-25
P-Card Receipts to BSC (final day) | Jerrod M | Finance Directors | 2014-06-26
P-Card Approvals done | All | Finance Directors | 2014-06-30
Complete Recurring Purchase Orders (Purchasing) | Katie |  | 2014-06-30
GL Roll (about 4pm) | Michon | Doit | 2014-06-30
PO Batch Close Process (after GL roll) | Suzanne | Doit | 2013-06-30
Encumbrance Roll (after Batch Close processes) | Suzanne | Doit | 2013-06-30
Switch old/new FY | Doit | Doit | 2014-06-30
Monthly 7 Paydate | Goldie | Payroll | 2013-07-01
Cost Monthly 7 | Goldie/Suzanne | Payroll | 2013-07-02
Cash deposit cutoff | Pam |  | 2012-07-02
All Receiving for June Completed in CUBuyplus | All | Finance Directors | 2013-07-02
Journal entries to Accounting Services- by noon | Michon | Finance Directors | 2012-07-03
Biweekly 14 Pay Date | Goldie | Payroll | 2014-07-03
Cost Biweely 14 | Goldie/Suzanne | Payroll | 2014-07-07
FPC Pay Date | Goldie | Payroll | 2014-07-07
Cost FPC 7 | Leisha | Payroll | 2013-07-07
Accrual entries from BSC - Items In CUBuyplus | Katie/Linda | Finance Directors | 2013-07-07
Accrual entries from departments - end of day | Leisha | Finance Directors | 2014-07-08
2nd payroll interface for monthly payroll for adjustments as needed | Goldie/Suzanne | Payroll | 2014-07-08
Finish Plant funds entries | Susan and Michon |  | 2014-07-08
Run PTO Carryforward | Cathy Harrahill | Payroll | 2014-07-08
Update fringe tables for new rates | Cathy H/Goldie | Payroll | 2014-07-08
Close Period 12 | Michon | Finance Directors | 2014-07-09
Run Preliminary reports | All | Finance Directors | 2014-07-09
CRUOPAL daily begins | Automatic | Doit | 2014-07-09
Between 12 and 14 fixes | Doit | Doit | 2014-07-10
Begin Biweekly 15 Run | Goldie | Payroll | 2014-07-14
Biweekly 15 Pay Date | Goldie | Payroll | 2014-07-18
Material journal entries (except FPC entry from Ray) to Michon by EOD - will post to period 14 | Michon | Finance Directors | 2014-07-16
FPC Journal Entries to Accounting Services – by noon. | Ray |  | 2014-07-19
Cost Biweekly 15 | Goldie/Suzanne | Payroll | 2014-07-21
BAN8 Budget Roll Test | Michon | Doit | 2014-07-23
Before Final 14 Fixes | Suzanne | Doit | 2014-07-24
Close period 14 | Michon | Finance Directors | 2014-07-24
After Final 14 Fixes | Suzanne | Doit | 2014-07-25
Budget Roll | Michon | Doit | 2014-07-28
Biweekly 16 Pay Date | Goldie | Payroll | 2014-08-01
Cost Biweekly 16 | Goldie/Suzanne | Payroll | 2013-08-04
Close period 1 in FY 14 | Michon |  | 2013-08-08
Prior Yr Daily -- Weekly | Michon | Doit | 2014-08-22
Start final audit work (through 9-23-11) |  | Finance Directors | 2014-08-25
Turn off prior yr | Michon | Doit | 2014-09-26
CRUOPAL daily ends $bansruns/cruopal.run | Michon or Suzanne | Doit | 2013-10-01
Drop oldest CRUOPAL fy $(Banrpts)/bld CRUOPAL.shl | Michon or Suzanne | Doit | 2013-10-01
Board Meeting |  |  | November
Note on E41: Creighton University DoIT: Confirmed with Jerrod M 4/7/14
Note on E69: Creighton University DoIT: Confirmed with Rosie
Note on E73: Creighton University DoIT: confirmed with Rosie
Note on E77: Creighton University DoIT: Day 4
Note on E79: Creighton University DoIT: Day 5
Note on E81: Creighton University DoIT: Day 5
Note on E83: Creighton University DoIT: Day 5
Note on E85: Creighton University DoIT: Day 5